## Schedule of Events
Phase | Event Description | Start Date | End Date | Standard | Accommodations | Online | Paper | State | DTC | TC | TAC | Tech | RS | P
Training Opportunities | Attend a Q&A session about accommodations and supports. 10:00 a.m. Central Time Register for Accommodations and Supports Webinar [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2024-10-29 | 2024-10-29 |  | x | x | x |  | x | x
Training Opportunities | Attend an office hour for new test coordinators. 1:00 p.m. Central Time Register for New Test Coordinators Office Hours [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2024-11-06 | 2024-11-06 | x | x | x | x |  | x | x
Training Opportunities | Attend first test administration webinar and Q&A session. 1:00 p.m. Central Time Register for First Test Administration Webinar [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2024-11-19 | 2024-11-19 | x | x | x | x |  | x | x
Training Opportunities | Attend an office hour on accommodations and supports. 11:00 a.m. Central Time Resister for Accommodations and Supports Office Hour [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2024-12-03 | 2024-12-03 |  | x | x | x |  | x | x
Training Opportunities | Attend a Q&A session about online testing. 10:00 a.m. Central Time Register for Online Testing Webinar [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2025-01-07 | 2025-01-07 | x | x | x | x |  |  | x |  | x
Training Opportunities | Attend an office hour on verifying student information. 10:00 a.m. Central Time Register for Verifying Student Information Office Hour [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2025-01-21 | 2025-01-21 | x | x | x | x |  | x | x
Training Opportunities | Attend second test administration webinar and Q&A session. Note: Not a duplicate of first test administration webinar. 10:00 a.m. Central Time Register for Second Test Administration Webinar [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2025-02-11 | 2025-02-11 | x | x | x | x |  | x | x
Training Opportunities | Attend an office hour on testing virtual school students. 10:00 a.m. Central Time Register for Testing Virtual School Students Office Hour [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2025-02-18 | 2025-02-18 | x | x | x | x |  | x | x
Training Opportunities | Attend an office hour on trusted agents and online reporting. 10:00 a.m. Central Time Register for Trusted Agent and Online Reporting Office Hour [https://event.on24.com/eventRegistration/EventLobbyServlet?target=reg20.jsp&eventid=4736823&sessionid=1&key=D805BA0E3312CCA1677A54804FCBCBAB&groupId=5754124&sourcepage=register] | 2025-04-08 | 2025-04-08 | x | x | x | x |  | x | x
Requesting Accommodations | Request ACT-authorized accommodations and/or supports for eligible examinees through the Test Accessibility and Accommodations System (TAA). Associate your test date with the request in TAA for students previously authorized for an accommodation. Note: Schools that participated in ACT District testing in fall 2024 can request ACT-authorized accommodations and/or supports beginning on November 11. Access TAA at Test Accessibility and Accommodations System (TAA) [https://success.act.org]. See the TAA User Guide [https://www.act.org/content/dam/act/unsecured/documents/user-guide-test-accessibility-and-accommodations.pdf] for more information. | 2024-09-16 | 2025-01-24 |  | x | x | x |  |  | x | x
Requesting Accommodations | Request reconsideration of ACT-authorized accommodations and/or supports in TAA. Associate your test date with the request in TAA for students previously authorized for an accommodation. | 2024-09-16 | 2025-01-31 |  | x | x | x |  |  | x | x
Requesting Accommodations | Request qualified exceptions to the deadline for ACT-authorized accommodations and/or supports for eligible examinees in TAA using the Qualified Exceptions to the Deadline [https://www.act.org/content/dam/act/unsecured/documents/ACTAccomsandELSupports-LateConsiderationform.pdf] form. There is not a reconsideration window for the qualified exceptions deadline. Note: Materials will be sent for students who are approved during this window. Verify all required documentation is uploaded into TAA, including the completed form, before selecting submit in TAA. | 2025-01-27 | 2025-03-07 |  | x | x | x |  |  | x | x
Requesting Accommodations | Request qualified exceptions to the deadline for ACT-authorized accommodations and/or supports for eligible examinees for Test Window 2 in TAA using the Qualified Exceptions to the Deadline [https://www.act.org/content/dam/act/unsecured/documents/ACTAccomsandELSupports-LateConsiderationform.pdf] form. There is not a reconsideration window for the qualified exceptions deadline. Verify all required documentation is uploaded into TAA, including the completed form, before selecting submit in TAA. Contact ACT to obtain the Make-up Order form for accommodations and supports if your site's initial selected test date has passed. | 2025-03-11 | 2025-03-14 |  | x | x | x |  |  | x | x
Prepare for Testing | Select test dates and shipping dates and verify your shipping address using the survey emailed to TCs and DTCs. Create accounts and invite users for online testing only in PearsonAccessnext. Submit the Address Change Request webform [https://www.act.org/content/act/en/products-and-services/state-and-district-solutions/address-change-request-form.html], if necessary. Contact DPI if a change in address is needed. | 2024-11-18 | 2025-01-10 | x | x | x | x |  | x | x
Prepare for Testing | Complete Site Readiness, including mock administration. | 2024-12-02 | 2025-02-05 | x | x | x | x |  |  | x |  | x
Prepare for Testing | Validate configuration and freeze test environment for online testing. Note: Additional details can be found in the ACT Technical Guide for Online Testing [https://www.act.org/content/dam/act/unsecured/documents/TechnicalGuidefortheACTTakenOnline.pdf]. | 2024-12-02 | 2025-02-05 | x | x | x | x |  |  | x |  | x
Prepare for Testing | Upload student data in PearsonAccessnext. | 2025-01-24 | 2025-01-24 | x | x | x | x | x
Prepare for Testing | Verify enrollment, complete an enroll, and review student identifying information and correct if needed. Note: Barcode labels will be sent for students assigned to paper testing and to the test event by January 31. | 2025-01-27 | 2025-01-31 | x | x | x | x |  |  | x
Prepare for Test Window 1 | Verify enrollment, complete an enroll request, and review student identifying information and correct if needed. | 2025-01-27 | 2025-02-28 | x | x | x | x |  | x | x
Prepare for Test Window 1 | Order additional standard time materials for use in this test window in PearsonAccessnext. | February 10–28 2025 | February 10–28 2025 | x |  | x | x |  | x | x
Prepare for Test Window 1 | Create and assign students to test sessions for online testing. | 2025-02-10 | 2025-03-21 | x | x | x | x |  |  | x
Prepare for Test Window 1 | Receive materials for testing based on the materials receipt week selected in PearsonAccessnext. Note: Ensure staff are available to receive the material shipment by monitoring the tracking and scheduled delivery. | February 17, 2025 | February 20, 2025 | x | x | x | x |  |  | x
Prepare for Test Window 1 | Receive materials for testing based on the materials receipt week selected in PearsonAccessnext. Note: Ensure staff are available to receive the material shipment by monitoring the tracking and scheduled delivery. | 2025-02-24 | 2025-02-27 | x | x | x | x |  |  | x
Prepare for Test Window 1 | Train room supervisors and proctors. | 2025-02-17 | 2025-03-10 | x | x | x | x |  |  | x
Prepare for Test Window 1 | Prepare rooms and materials. | 2025-02-17 | 2025-03-10 | x | x | x | x |  |  | x
Prepare for Test Window 1 | Distribute MyACT non-test instructions and Taking the ACT to all students. Students must complete the non-test information in MyACT. Note: Students have an additional two calendar days after they finish testing to complete their non-test information in MyACT. | 2025-02-17 | 2025-03-10 | x | x | x | x |  |  | x
Prepare for Test Window 1 | Print the Accommodations and Supports Roster to prepare for testing with accommodations and/or supports. | 2025-03-03 | 2025-03-10 |  | x | x | x |  |  | x
Prepare for Test Window 1 | Prepare online test sessions in PearsonAccessnext. | 2025-03-07 | 2025-03-21 | x | x | x | x |  |  | x |  | x
Prepare for Test Window 1 | Administer the ACT on paper with standard time. | 2025-03-11 | 2025-03-11 | x |  | x | x |  |  | x |  |  | x | x
Prepare for Test Window 1 | Administer the ACT on paper with accommodations and/or supports. Note: Testing must not be administered on the weekends. | March 11, 2025 | March 14, 2025 |  | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 1 | Administer the ACT on paper with accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-03-17 | 2025-03-21 |  | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 1 | Start online test sessions in PearsonAccessnext. Administer the ACT online with standard time or accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-03-11 | March 14, 2025 | x | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 1 | Start online test sessions in PearsonAccessnext. Administer the ACT online with standard time or accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-03-17 | 2025-03-21 | x | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 1 | Return Paper Standard Testing Materials: Have all materials ready to be picked up the day after testing is complete (test booklets, used answer documents, and room roster reports). If your materials have not been picked up within three days, contact FedEx. Keep unused answer documents for future test date. Receipt deadline at ACT: March 18, 2025 Note: Late-arriving answer documents will not be scored. | 2025-03-12 | 2025-03-12 | x |  | x | x |  | x | x
Prepare for Test Window 1 | Return Paper Accommodations/Supports Testing Materials: Have all materials ready to be picked up the day after the testing window closes (test booklets, used answer documents, and room roster reports). If your materials have not been picked up within three days, contact FedEx. Keep unused answer documents for future test date. Receipt deadline at ACT: March 28, 2025 Note: Late-arriving answer documents will not be scored. | 2025-03-24 | 2025-03-24 |  | x | x | x |  | x | x
Prepare for Test Window 2 | Verify enrollment, complete an enroll request, and review student identifying information and correct if needed. | 2025-01-27 | 2025-03-14 | x | x | x | x |  |  | x
Prepare for Test Window 2 | Receive initial materials if you selected Test Window 2 as your first test window. Note: Ensure staff are available to receive the material shipment by monitoring the tracking and scheduled delivery. | 2025-03-03 | 2025-03-06 | x | x | x | x |  |  | x
Prepare for Test Window 2 | Receive initial materials if you selected Test Window 2 as your first test window. Note: Ensure staff are available to receive the material shipment by monitoring the tracking and scheduled delivery. | 2025-03-10 | 2025-03-13 | x | x | x | x |  |  | x
Prepare for Test Window 2 | Distribute MyACT non-test instructions and Taking the ACT to all students. Students must complete the non-test information in MyACT. Note: Students have an additional two calendar days after they finish testing to complete their non-test information in MyACT. | 2025-03-03 | 2025-03-25 | x | x | x | x |  |  | x
Prepare for Test Window 2 | Order additional standard time materials for use in this test window in PearsonAccessnext. | 2025-03-11 | 2025-03-14 | x |  | x | x |  | x | x
Prepare for Test Window 2 | Order accommodations and/or supports materials for use in this test window by calling ACT Accommodations at 800.553.6244, ext. 1788. | 2025-03-11 | 2025-03-14 |  | x | x | x |  | x | x
Prepare for Test Window 2 | Receive make-up test materials for Test Window 2 if your initial testing occurred in Test Window 1. Note: Ensure staff are available to receive the material shipment by monitoring the tracking and scheduled delivery. | 2025-03-17 | 2025-03-20 | x | x | x | x |  |  | x
Prepare for Test Window 2 | Print the Accommodations and Supports Roster to prepare for testing with accommodations and/or supports. | 2025-03-17 | 2025-03-24 |  | x | x | x |  |  | x
Prepare for Test Window 2 | Create and assign students to test sessions for online testing. | 2025-03-19 | 2025-04-04 | x | x | x | x |  |  | x
Prepare for Test Window 2 | Prepare online test sessions in PearsonAccessnext. | 2025-03-21 | 2025-04-04 | x | x | x | x |  |  | x |  | x
Prepare for Test Window 2 | Administer the ACT on paper with standard time. | 2025-03-25 | 2025-03-25 | x |  | x | x |  |  | x |  |  | x | x
Prepare for Test Window 2 | Administer the ACT on paper with accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-03-25 | 2025-03-28 |  | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 2 | Administer the ACT on paper with accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-03-31 | 2025-04-04 |  | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 2 | Start online test sessions in PearsonAccessnext. Administer the ACT online with standard time or accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-03-25 | 2025-03-28 | x | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 2 | Start online test sessions in PearsonAccessnext. Administer the ACT online with standard time or accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-03-31 | 2025-04-04 | x | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 2 | Return Paper Standard Testing Materials: Have all materials ready to be picked up the day after testing is complete (test booklets, used answer documents, and room roster reports). If your materials have not been picked up within three days, contact FedEx. Keep unused answer documents for future test date. Receipt deadline at ACT: April 1, 2025 Note: Late-arriving answer documents will not be scored. | 2025-03-26 | 2025-03-26 | x |  | x | x |  | x | x
Prepare for Test Window 2 | Return Paper Accommodations/Supports Testing Materials: Have all materials ready to be picked up the day after the testing window closes (test booklets, used answer documents, and room roster reports). If your materials have not been picked up within three days, contact FedEx. Keep unused answer documents for future test date. Receipt deadline at ACT: April 11, 2025 Note: Late-arriving answer documents will not be scored. | 2025-04-07 | 2025-04-07 |  | x | x | x |  | x | x
Prepare for Test Window 3 | Order standard time materials for use in this test window in PearsonAccessnext. | 2025-03-25 | 2025-03-28 | x |  | x | x |  | x | x
Prepare for Test Window 3 | Order accommodations and/or supports materials for use in this test window by calling ACT Accommodations at 800.553.6244, ext. 1788. | 2025-03-25 | 2025-03-28 |  | x | x | x |  | x | x
Prepare for Test Window 3 | Verify enrollment, complete an enroll request, and review student identifying information and correct if needed. | 2025-01-27 | 2025-03-28 | x | x | x | x |  |  | x
Prepare for Test Window 3 | Receive materials for testing. Note: Ensure staff are available to receive the material shipment by monitoring the tracking and scheduled delivery. | 2025-03-31 | 2025-04-03 | x | x | x | x |  |  | x
Prepare for Test Window 3 | Distribute MyACT non-test instructions and Taking the ACT to all students. Students must complete the non-test information in MyACT. Note: Students have an additional two calendar days after they finish testing to complete their non-test information in MyACT. | 2025-03-31 | 2025-04-07 | x | x | x | x |  |  | x
Prepare for Test Window 3 | Print the Accommodations and Supports Roster to prepare for testing with accommodations and/or supports. | 2025-03-31 | 2025-04-07 |  | x | x | x |  |  | x
Prepare for Test Window 3 | Create and assign students to test sessions for online testing. | 2025-04-02 | 2025-04-18 | x | x | x | x |  |  | x
Prepare for Test Window 3 | Prepare online test sessions in PearsonAccessnext. | 2025-04-04 | 2025-04-18 | x | x | x | x |  |  | x |  | x
Prepare for Test Window 3 | Administer the ACT on paper with standard time. | 2025-04-08 | 2025-04-08 | x |  | x | x |  |  | x |  |  | x
Prepare for Test Window 3 | Administer the ACT on paper with accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-04-08 | 2025-04-11 |  | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 3 | Administer the ACT on paper with accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-04-14 | 2025-04-18 |  | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 3 | Start online test sessions in PearsonAccessnext. Administer the ACT online with standard time or accommodations and/or supports. Note: Testing must not be administered on the weekends. | April 8, 2025 | April 11, 2025 | x | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 3 | Start online test sessions in PearsonAccessnext. Administer the ACT online with standard time or accommodations and/or supports. Note: Testing must not be administered on the weekends. | 2025-04-14 | 2025-04-18 | x | x | x | x |  |  | x | x |  | x | x
Prepare for Test Window 3 | Return Paper Standard Testing Materials: Have all materials ready to be picked up the day after testing is complete (test booklets, used answer documents, and room roster reports). If your materials have not been picked up within three days, contact FedEx. Keep unused answer documents for future test date. Receipt deadline at ACT: April 15, 2025 Note: Late-arriving answer documents will not be scored. | 2025-04-09 | 2025-04-09 | x |  | x | x |  |  | x
Prepare for Test Window 3 | Return Paper Accommodations/Supports Testing Materials: Have all materials ready to be picked up the day after the testing window closes (test booklets, used answer documents, and room roster reports). If your materials have not been picked up within three days, contact FedEx. Keep unused answer documents for future test date. Receipt deadline at ACT: April 25, 2025 Note: Late-arriving answer documents will not be scored. | 2025-04-21 | 2025-04-21 |  | x | x | x |  |  | x